NEC3 Engineering & Construction Contract

| Between | ESKOM HOLDINGS SOC Ltd (Reg No. 2002/015527/30) |  |
| --- | --- | --- |
| and | [Insert at award stage] (Reg No. ___________) |  |
| for | Design, Supply, Installation of Solar PV Carports and Battery Energy Storage System at Eskom Academy of Learning Project Insert title of the works |  |
| Contents: |  | No of pages |
| Part C1 | Agreements & Contract Data | [2] |
| Part C2 | Pricing Data | [44] |
| Part C3 | Scope of Work | [48] |
| Part C4 | Site Information | [76] |
| CONTRACT No. | [Insert at award stage] |  |

Part C1: Agreements & Contract Data

| Contents: |  | No of pages |
| --- | --- | --- |
| C1.1 | Form of Offer and Acceptance [to be inserted from Returnable Documents at award stage] | [2] |
| C1.2a | Contract Data provided by the Employer | [44] |
| C1.2b | Contract Data provided by the Contractor [to be inserted from Returnable Documents at award stage] | [48] |
| C1.3 | Proforma Guarantees | [76] |

C1.1 Form of Offer & Acceptance

## Offer

The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of:

Design, Supply, Installation of Solar PV Carports and Battery Energy Storage System at Eskom Academy of Learning Project

The tenderer, identified in the Offer signature block, has examined the documents listed in the Tender Data and addenda thereto and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

Delete the Options which do not apply

| Options A, | The offered total of the Prices exclusive of VAT is | R [●] |
| --- | --- | --- |
|  | The first forecast of the total Defined Cost plus the Fee exclusive of VAT is | R [●] |
|  | Sub total | R [●] |
|  | Value Added Tax @ 15% is | R [●] |
|  | The offered total of the amount due inclusive of VAT is | R [●] |
|  | (in words) [●] |  |

This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| For the tenderer: |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |
| Tenderer’s CIDB registration number (if applicable) |  |  |  |  |

## Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an agreement between the Employer and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in:

Part C1		Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part C2		Pricing Data

Part C3		Scope of Work: Works Information

Part C4		Site Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule.

The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed original copy signed between them of this document, including the Schedule of Deviations (if any).

Unless the tenderer (now Contractor) within five working days of the date of such receipt notifies the Employer in writing of any reason why he cannot accept the contents of this agreement, this agreement shall constitute a binding contract between the Parties.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| for the Employer | Eskom Holdings SOC Ltd, 1 Maxwell Drive, Sunninghill, Sandton, 2157 |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |

Note: If a tenderer wishes to submit alternative tenders, use another copy of this Form of Offer and Acceptance.

## Schedule of Deviations to be completed by the Employer prior to contract award

Note:

- This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.

- The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

- A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

| No. | Subject | Details |
| --- | --- | --- |
| 1 | Not Applicable[●] | Not Applicable[●] |
| 2 | [●] | [●] |
| 3 | [●] | [●] |
| 4 | [●] | [●] |
| 5 | [●] | [●] |
| 6 | [●] | [●] |
| 7 | [●] | [●] |

By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement.

|  | #### For the tenderer: |  | #### For the Employer |
| --- | --- | --- | --- |
| Signature |  |  |  |
| Name |  |  |  |
| Capacity |  |  |  |
| On behalf of | (Insert name and address of organisation) |  | (Insert name and address of organisation) Eskom Holdings SOC Ltd, 1 Maxwell Drive, Sunninghill, Sandton, 2157 |
| Name & signature of witness |  |  |  |
| Date |  |  |  |

C1.2 ECC3 Contract Data

# Part one - Data provided by the Employer

Completion of the data in full, according to the Options chosen, is essential to create a complete contract.

| ## Clause | ## Statement | ## Data |
| --- | --- | --- |
| 1 | ## General |  |
|  | The conditions of contract are the core clauses and the clauses for main Option |  |
|  |  | A: Priced contract with activity schedule |
|  | dispute resolution Option | W1: Dispute resolution procedure |
|  | and secondary Options |  |
|  |  | X1: Price adjustment for inflation |
|  |  | X2 Changes in the law |
|  |  | X7: Delay damages |
|  |  | X12: Partnering |
|  |  | X16: Retention |
|  |  | X17: Low performance damages |
|  |  | X18: Limitation of liability |
|  |  | Z: Additional conditions of contract |
|  | of the NEC3 Engineering and Construction Contract, April 2013 (ECC3) | If 2005 Edition is to be used delete “April 2013” and replace with “June 2005 with amendments June 2006”. Always delete this note before finalising this Data |

| 10.1 |  | The Employer is (Name): |  | Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state owned company incorporated in terms of the company laws of the Republic of South Africa |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Address |  | Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg |  |  |  |  |  |  |  |
| 10.1 |  | The Project Manager is: (Name) |  | Kameel Burath |  |  |  |  |  |  |  |
|  |  | Address |  | Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg |  |  |  |  |  |  |  |
|  |  | Tel |  | +27 11 800 4660 |  |  |  |  |  |  |  |
|  |  | Fax |  | N/A |  |  |  |  |  |  |  |
|  |  | e-mail |  | BurathK@eskom.co.za |  |  |  |  |  |  |  |
| 10.1 |  | The Supervisor is: (Name) |  | TBC |  |  |  |  |  |  |  |
|  |  | Address |  | TBC |  |  |  |  |  |  |  |
|  |  | Tel No. |  | TBC |  |  |  |  |  |  |  |
|  |  | Fax No. |  | TBC |  |  |  |  |  |  |  |
|  |  | e-mail |  | TBC |  |  |  |  |  |  |  |
| 11.2(13) |  | The works are |  | Design, Supply, Installation of Solar PV Carports and Battery Energy Storage System at Eskom Academy of Learning Project |  |  |  |  |  |  |  |
| 11.2(14) |  | The following matters will be included in the Risk Register |  | - The contractor will need to be aware that the site will be operational during construction and should provide the necessary security measures to ensure that security is not compromised. - Further risks to be identified at the initial project meeting and on an ongoing basis. - The contractor will need to be aware of the Eskom security requirements and standard that must be adhered to and comply with. - Conditional assessment to be conducted and accepted by Eskom representatives, prior to start on site. This includes design reviews. - Reputable OEM used with accredited installers, where required. - Limited as-built, operation and maintenance information |  |  |  |  |  |  |  |
| 11.2(15) |  | The boundaries of the site are |  | Eskom Academy of Learning Campus |  |  |  |  |  |  |  |
| 11.2(16) |  | The Site Information is in |  | Part 4: Site Information |  |  |  |  |  |  |  |
| 11.2(19) |  | The Works Information is in |  | Part 3: Scope of Work and all documents and drawings to which it makes reference. |  |  |  |  |  |  |  |
| 12.2 |  | The law of the contract is the law of |  | the Republic of South Africa |  |  |  |  |  |  |  |
| 13.1 |  | The language of this contract is |  | English |  |  |  |  |  |  |  |
| 13.3 |  | The period for reply is |  | Five (5) working days |  |  |  |  |  |  |  |
| ## 2 |  | ## The Contractor's main responsibilities |  | Data required by this section of the core clauses is provided by the Contractor in Part 2 and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |
| ## 3 |  | ## Time |  |  |  |  |  |  |  |  |  |
| 11.2(3) |  | The completion date for the whole of the works is |  | 5 Months from Site Handover |  |  |  |  |  |  |  |
| 11.2(9) |  | The key dates and the conditions to be met are: |  | Condition to be met |  |  |  |  |  |  | key date |
|  |  |  | 1 |  | Notice of construction be given to Department of Labour |  |  |  |  |  | As per approved schedule |
|  |  |  | 2 |  | Security clearance of personnel and induction |  |  |  |  |  | As per approved schedule |
|  |  |  | 3 |  | Safety File Submission accepted, and staff induction completed |  |  |  |  |  | As per approved schedule |
|  |  |  | 4 |  | Formal notification of areas to work on and formal approval – EAL security |  |  |  |  |  | As per approved schedule |
|  |  |  | 5 |  | Design Freeze (Review and acceptance). |  |  |  |  |  | As per approved schedule |
|  |  |  | 6 7 8 9 10 |  | Mechanical Completion – When the Contractor completes the Mechanical Completion Test of the SPVC and BESS successfully (Technical Specification Section 3.7) Electrical Completion – When the Contractor completes the Electrical Completion Test (Technical Specification Section 3.7) Substantial Completion - The Provisional Acceptance Test (PAT) takes place once the Commissioning Certificate is issued (Technical Specification Section 3.9) Final Completion - The duration of the Final Acceptance Test (FAT) is 12-month period after the issuance of Substantial Completion Certificate (Technical Specification Section 3.9) Commissioning and Training |  |  |  |  |  | As per approved schedule As per approved schedule As per approved schedule As per approved schedule As per approved schedule |
|  |  |  |  |  | Hand Over |  |  |  |  |  | As per approved schedule |
| 30.1 |  | The access dates are: |  | Part of the Site |  |  |  |  |  | Date |  |
|  |  |  |  | 1 |  | Eskom Academy of Learning with all regulation approvals to access and work |  |  |  | Before execution of work |  |
| 31.1 |  | The Contractor is to submit a first programme for acceptance within |  | 1 week of the Contract Date. |  |  |  |  |  |  |  |
| 31.2 |  | The starting date is |  | 2 weeks after contract signing. |  |  |  |  |  |  |  |
| 32.2 |  | The Contractor submits revised programmes at intervals no longer than |  | 2 weeks. |  |  |  |  |  |  |  |
| 35.1 |  | The Employer is not willing to take over the works before the Completion Date. |  | All works are completed before the Employer takes over the works – full work completed |  |  |  |  |  |  |  |
| ## 4 |  | ## Testing and Defects |  |  |  |  |  |  |  |  |  |
| 42.2 |  | The defects date is |  | 52 weeks after Completion of the whole of the works. |  |  |  |  |  |  |  |
| 43.2 |  | The defect correction period is |  | One (1) week |  |  |  |  |  |  |  |
| ## 5 |  | ## Payment |  |  |  |  |  |  |  |  |  |
| 50.1 |  | The assessment interval is |  | On the 25 day of each successive month. |  |  |  |  |  |  |  |
| 51.1 |  | The currency of this contract is the |  | South African Rand. |  |  |  |  |  |  |  |
| 51.2 |  | The period within which payments are made is |  | 4 weeks |  |  |  |  |  |  |  |
| 51.4 |  | The interest rate is |  | the publicly quoted prime rate of interest (calculated on a 365 day year) charged from time to time by the Standard Bank of South Africa Limited (as certified, in the event of any dispute, by any manager of such bank, whose appointment it shall not be necessary to prove) for amounts due in Rands and (ii) the LIBOR rate applicable at the time for amounts due in other currencies. LIBOR is the 6 month London Interbank Offered Rate quoted under the caption “Money Rates” in The Wall Street Journal for the applicable currency or if no rate is quoted for the currency in question then the rate for United States Dollars, and if no such rate appears in The Wall Street Journal then the rate as quoted by the Reuters Monitor Money Rates Service (or such service as may replace the Reuters Monitor Money Rates Service) on the due date for the payment in question, adjusted mutatis mutandis every 6 months thereafter and as certified, in the event of any dispute, by any manager employed in the foreign exchange department of The Standard Bank of South Africa Limited, whose appointment it shall not be necessary to prove. |  |  |  |  |  |  |  |
| ## 6 |  | ## Compensation events |  |  |  |  |  |  |  |  |  |
| 60.1(13) |  | The place where weather is to be recorded is: |  | Midrand (Kaalfontein), Gauteng and surrounding areas to the site |  |  |  |  |  |  |  |
|  |  | The weather measurements to be recorded for each calendar month are, |  | the cumulative rainfall (mm) |  |  |  |  |  |  |  |
|  |  |  |  | the number of days with rainfall more than 10 mm |  |  |  |  |  |  |  |
|  |  |  |  | the number of days with minimum air temperature less than 0 degrees Celsius |  |  |  |  |  |  |  |
|  |  |  |  | the number of days with snow lying at 09:00 hours South African Time |  |  |  |  |  |  |  |
|  |  | The weather measurements are supplied by |  | The South African Weather Bureau at the nearest station next to the site. |  |  |  |  |  |  |  |
|  |  | The weather data are the records of past weather measurements for each calendar month which were recorded at: |  |  |  |  |  |  |  |  |  |
|  |  | and which are available from: |  | the South African Weather Bureau and included in Annexure A to this Contract Data provided by the Employer |  |  |  |  |  |  |  |
| 60.1(13) |  | Assumed values for the ten year return weather data for each weather measurement for each calendar month are: |  | As stated in Annexure A to this Contract Data provided by the Employer. Note: If this arrangement is used, delete the rows above for 60.1(13) and delete this note. |  |  |  |  |  |  |  |
| ## 7 |  | ## Title |  | There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |
| ## 8 |  | ## Risks and insurance |  |  |  |  |  |  |  |  |  |
| 80.1 |  | These are additional Employer's risks |  | 1. There are no additional risks |  |  |  |  |  |  |  |
| ## 9 |  | ## Termination |  | There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |
| ## 10 |  | ## Data for main Option clause |  |  |  |  |  |  |  |  |  |
| A |  | Priced contract with activity schedule |  | There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |
| ## 11 |  | ## Data for Option W1 |  |  |  |  |  |  |  |  |  |
| W1.1 |  | The Adjudicator is |  | the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him. (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA). |  |  |  |  |  |  |  |
|  |  | Address |  | [●]TBA |  |  |  |  |  |  |  |
|  |  | Tel No. |  | [●]TBA |  |  |  |  |  |  |  |
|  |  | Fax No. |  | [●]TBA |  |  |  |  |  |  |  |
|  |  | e-mail |  | [●]TBA |  |  |  |  |  |  |  |
| W1.2(3) |  | The Adjudicator nominating body is: |  | the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the London Institution of Civil Engineers. (See www.ice-sa.org.za ) or its successor body. |  |  |  |  |  |  |  |
| W1.4(2) |  | The tribunal is: |  | arbitration. |  |  |  |  |  |  |  |
| W1.4(5) |  | The arbitration procedure is |  | the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |  |  |  |  |
|  |  | The place where arbitration is to be held is |  | Gauteng in South Africa |  |  |  |  |  |  |  |
|  |  | The person or organisation who will choose an arbitrator - if the Parties cannot agree a choice or - if the arbitration procedure does not state who selects an arbitrator, is |  | the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |  |  |  |  |
| ## 12 |  | ## Data for secondary Option clauses |  |  |  |  |  |  |  |  |  |
| X1 |  | Price adjustment for inflation |  |  |  |  |  |  |  |  |  |
| X1.1(a) |  | The base date for indices is |  | CPI applicable if project is 12 months or more. Base date is one month prior to tender close |  |  |  |  |  |  |  |
| X1.1(c) |  | The proportions used to calculate the Price Adjustment Factor are: |  | proportion |  |  | linked to index for |  | Index prepared by |  |  |
|  |  |  |  | 0. [●] |  |  | [●] |  | [●] |  |  |
|  |  |  |  | 0. [●] |  |  | [●] |  | [●] |  |  |
|  |  |  |  | 0. [●] |  |  | [●] |  | [●] |  |  |
|  |  |  |  | 0. [●] |  |  | [●] |  | [●] |  |  |
|  |  |  |  | 0. [●] |  |  | [●] |  | [●] |  |  |
|  |  |  |  | 0.15 |  |  | non-adjustable |  |  |  |  |
|  |  | Total |  | 1.00 |  |  |  |  |  |  |  |
| X2 |  | Changes in the law |  | There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |
| X7 |  | Delay damages |  |  |  |  |  |  |  |  |  |
| X7.1 |  | Delay damages for Completion of the whole of the works are |  | R10,000.00 per day up to a limit of 20% of the Contract Value. |  |  |  |  |  |  |  |
| X12 |  | Partnering |  |  |  |  |  |  |  |  |  |
| X12.1(1) |  | The Client is (Name) |  | [●] |  |  |  |  |  |  |  |
|  |  | Address |  | [●] |  |  |  |  |  |  |  |
|  |  | Tel |  | [●] |  |  |  |  |  |  |  |
|  |  | Fax |  | [●] |  |  |  |  |  |  |  |
| X12.2(1) |  | The Client’s objective is. |  | [●] |  |  |  |  |  |  |  |
| X12.1(4) |  | The Partnering Information is in |  | [●] |  |  |  |  |  |  |  |
| X16 |  | Retention (not used with Option F) |  |  |  |  |  |  |  |  |  |
| X16.1 |  | The retention free amount is |  | R0.00. |  |  |  |  |  |  |  |
|  |  | The retention percentage is |  | 10% |  |  |  |  |  |  |  |
| X17 |  | Low performance damages |  |  |  |  |  |  |  |  |  |
| X17.1 |  | The amounts for low performance damages are: |  | Amount |  |  |  | Performance level |  |  |  |
|  |  |  |  | R 200,000.00 or cost of low performance damages stated |  |  |  | Including and not limited to the following: Poor workmanship, inferior material quality or failure to follow accepted Method Statements and Quality Control Plans (QCP). |  |  |  |
| X18 |  | Limitation of liability |  |  |  |  |  |  |  |  |  |
| X18.1 |  | The Contractor’s liability to the Employer for indirect or consequential loss is limited to: |  | R0.0 (zero Rand) |  |  |  |  |  |  |  |
| X18.2 |  | For any one event, the Contractor’s liability to the Employer for loss of or damage to the Employer’s property is limited to: |  | the amount of the deductibles relevant to the event |  |  |  |  |  |  |  |
| X18.3 |  | The Contractor’s liability for Defects due to his design which are not listed on the Defects Certificate is limited to |  | The greater of the total of the Prices at the Contract Date and - the amounts excluded and unrecoverable from the Employer’s assets policy for correcting the Defect (other than the resulting physical damage which is not excluded) plus the applicable deductible as at contract date. |  |  |  |  |  |  |  |
| X18.4 |  | The Contractor’s total liability to the Employer for all matters arising under or in connection with this contract, other than excluded matters, is limited to: |  | the total of the Prices other than for the additional excluded matters. The Contractor’s total liability for the additional excluded matters is not limited. The additional excluded matters are amounts for which the Contractor is liable under this contract for Defects due to his design which arise before the Defects Certificate is issued, Defects due to manufacture and fabrication outside the Site, loss of or damage to property (other than the works, Plant and Materials), death of or injury to a person and infringement of an intellectual property right. |  |  |  |  |  |  |  |
| X18.5 |  | The end of liability date is |  | (i) Seven 7 years after the defects date for latent Defects and (ii) the date on which the liability in question prescribes in accordance with the Prescription Act No. 68 of 1969 (as amended or in terms of any replacement legislation) for any other matter. A latent Defect is a Defect which would not have been discovered on reasonable inspection by the Employer or the Supervisor before the defects date, without requiring any inspection not ordinarily carried out by the Employer or the Supervisor during that period. If the Employer or the Supervisor do undertake any inspection over and above the reasonable inspection, this does not place a greater responsibility on the Employer or the Supervisor to have discovered the Defect. |  |  |  |  |  |  |  |
| Z |  | The Additional conditions of contract are |  | Z1 to Z15 always apply. |  |  |  |  |  |  |  |
| Z1 | Cession delegation and assignment |  |  |  |  |  |  |  |  |  |  |
| Z1.1 | The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer. |  |  |  |  |  |  |  |  |  |  |
| Z1.2 | Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. |  |  |  |  |  |  |  |  |  |  |
| Z2 | Joint ventures |  |  |  |  |  |  |  |  |  |  |
| Z2.1 | If the Contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract. |  |  |  |  |  |  |  |  |  |  |
| Z2.2 | Unless already notified to the Employer, the persons or organisations notify the Project Manager within two weeks of the Contract Date of the key person who has the authority to bind the Contractor on their behalf. |  |  |  |  |  |  |  |  |  |  |
| Z2.3 | The Contractor does not alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Contractor in writing. |  |  |  |  |  |  |  |  |  |  |
| Z3 |  | Change of Broad Based Black Economic Empowerment (B-BBEE) status |  |  |  |  |  |  |  |  |  |
| Z3.1 |  | Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change. |  |  |  |  |  |  |  |  |  |
| Z3.2 |  | The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Project Manager within thirty days of the notification or as otherwise instructed by the Project Manager. |  |  |  |  |  |  |  |  |  |
| Z3.3 |  | Where, as a result, the Contractor’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Works. |  |  |  |  |  |  |  |  |  |
| Z3.4 |  | Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are P1, P2 and P3 as stated in clause 92, and the amount due is A1 and A3 as stated in clause 93. |  |  |  |  |  |  |  |  |  |
| Z4 | Confidentiality |  |  |  |  |  |  |  |  |  |  |
| Z4.1 | The Contractor does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time). Should the Contractor disclose information to Others in terms of clause 25.1, the Contractor ensures that the provisions of this clause are complied with by the recipient. |  |  |  |  |  |  |  |  |  |  |
| Z4.2 | If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Project Manager. |  |  |  |  |  |  |  |  |  |  |
| Z4.3 | In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed. |  |  |  |  |  |  |  |  |  |  |
| Z4.4 | The taking of images (whether photographs, video footage or otherwise) of the works or any portion thereof, in the course of Providing the Works and after Completion, requires the prior written consent of the Project Manager. All rights in and to all such images vests exclusively in the Employer. |  |  |  |  |  |  |  |  |  |  |
| Z4.5 | The Contractor ensures that all his subcontractors abide by the undertakings in this clause. |  |  |  |  |  |  |  |  |  |  |
| Z5 | Waiver and estoppel: Add to core clause 12.3: |  |  |  |  |  |  |  |  |  |  |
| Z5.1 | Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, the Project Manager, the Supervisor, or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing. |  |  |  |  |  |  |  |  |  |  |
| Z6 |  | Health, safety and the environment: Add to core clause 27.4 |  |  |  |  |  |  |  |  |  |
| Z6.1 |  | The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the works. Without limitation the Contractor: accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2014 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Site; warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of works; and undertakes, in and about the execution of the works, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |  |  |  |  |  |
| Z6.2 |  | The Contractor, in and about the execution of the works, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |  |  |  |  |  |
| Z7 | Provision of a Tax Invoice and interest. Add to core clause 51 |  |  |  |  |  |  |  |  |  |  |
| Z7.1 | Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Works Information, showing the amount due for payment equal to that stated in the payment certificate. |  |  |  |  |  |  |  |  |  |  |
| Z7.2 | If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice. Interest due by the Employer in terms of core clause 51.2 is then calculated from the delayed date by when payment is to be made. |  |  |  |  |  |  |  |  |  |  |
| Z7.3 | The Contractor (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment. |  |  |  |  |  |  |  |  |  |  |
| Z8 | Notifying compensation events |  |  |  |  |  |  |  |  |  |  |
| Z8.1 | Delete from the last sentence in core clause 61.3, “unless the Project Manager should have notified the event to the Contractor but did not”. |  |  |  |  |  |  |  |  |  |  |
| Z9 | Employer’s limitation of liability |  |  |  |  |  |  |  |  |  |  |
| Z9.1 | The Employer’s liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand) |  |  |  |  |  |  |  |  |  |  |
| Z9.2 | The Contractor’s entitlement under the indemnity in 83.1 is provided for in 60.1(14) and the Employer’s liability under the indemnity is limited. |  |  |  |  |  |  |  |  |  |  |
| Z10 | Termination: Add to core clause 91.1, at the second main bullet point, fourth sub-bullet point, after the words "against it": |  |  |  |  |  |  |  |  |  |  |
| Z10.1 | or had a business rescue order granted against it. |  |  |  |  |  |  |  |  |  |  |
| Z11 | Addition to secondary Option X7 Delay damages (if applicable in this contract) |  |  |  |  |  |  |  |  |  |  |
| Z11.1 | If the amount due for the Contractor’s payment of delay damages reaches the limits stated in this Contract Data for Option X7 or Options X5 and X7 used together, the Employer may terminate the Contractor’s obligation to Provide the Works using the same procedures and payment on termination as those applied for reasons R1 to R15 or R18 stated in the Termination Table. |  |  |  |  |  |  |  |  |  |  |

| Z12 | Ethics |  |
| --- | --- | --- |
| For the purposes of this Z-clause, the following definitions apply: |  |  |
| Affected Party |  | means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subcontractors or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends, |
| Coercive Action |  | means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally, |
| Collusive Action |  | means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally, |
| Committing Party |  | means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractor or the Subcontractor’s employees, |
| Corrupt Action |  | means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party, |
| Fraudulent Action |  | means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation, |
| Obstructive Action |  | means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action, and |
| Prohibited Action |  | means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action. |
| Z12.1 | A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof. |  |
| Z12.2 | The Employer may terminate the Contractor’s obligation to Provide the Services if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Services for this reason. |  |
| Z12.3 | If the Employer terminates the Contractor’s obligation to Provide the Services for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2. |  |
| Z12.4 | A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation. |  |
| Z13 | Insurance |  |
| Z 13.1 | Replace core clause 84 with the following: |  |

| Insurance cover | 84 |  |
| --- | --- | --- |
|  | 84.1 | When requested by a Party, the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force. |
|  | 84.2 | The Contractor provides the insurances stated in the Insurance Table A. |
|  | 84.3 | The insurances provide cover for events which are at the Contractor’s risk from the starting date until the earlier of Completion and the date of the termination certificate. |
|  |  | ### INSURANCE TABLE A Insurance against; Minimum amount of cover or minimum limit of indemnity. Loss of or damage to the works, Plant and Materials; The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance. Loss of or damage to Equipment; The replacement cost. Liability for loss of or damage to property (except the works, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) caused by activity in connection with this contract; Loss of or damage to property Employer’s property The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance Other property The replacement cost Bodily injury to or death of a person The amount required by applicable law. Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract; The amount required by the applicable law. |
| Z 13.2 |  | Replace core clause 87 with the following: The Employer provides the insurances stated in the Insurance Table B. |
|  |  | #### INSURANCE TABLE B Insurance against or name of policy; Minimum amount of cover or minimum limit of indemnity. Assets All Risk; Per the insurance policy document. Contract Works insurance; Per the insurance policy document. Environmental Liability; Per the insurance policy document. General and Public Liability; Per the insurance policy document. Transportation (Marine); Per the insurance policy document. Motor Fleet and Mobile Plant; Per the insurance policy document. Terrorism; Per the insurance policy document. Cyber Liability; Per the insurance policy document. Nuclear Material Damage and Business Interruption; Per the insurance policy document. Nuclear Material Damage Terrorism; Per the insurance policy document. |

| Z14 | Nuclear Liability |  |
| --- | --- | --- |
| Z14.1 | The Employer is the operator of the Koeberg Nuclear Power Station (KNPS), a nuclear installation, as designated by the National Nuclear Regulator of the Republic of South Africa, and is the holder of a nuclear licence in respect of the KNPS. |  |
| Z14.2 | The Employer is solely responsible for and indemnifies the Contractor or any other person against any and all liabilities which the Contractor or any person may incur arising out of or resulting from nuclear damage, as defined in Act 47 of 1999, save to the extent that any liabilities are incurred due to the unlawful intent of the Contractor or any other person or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |
| Z14.3 | Subject to clause Z14.4 below, the Employer waives all rights of recourse, arising from the aforesaid, save to the extent that any claims arise or liability is incurred due or attributable to the unlawful intent of the Contractor or any other person, or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |
| Z14.4 | The Employer does not waive its rights provided for in section 30 (7) of Act 47 of 1999, or any replacement section dealing with the same subject matter. |  |
| Z14.5 | The protection afforded by the provisions hereof shall be in effect until the KNPS is decommissioned. |  |
| Z15 | Asbestos |  |
| For the purposes of this Z-clause, the following definitions apply: |  |  |
| AAIA |  | means approved asbestos inspection authority. |
| ACM |  | means asbestos containing materials. |
| AL |  | means action level, i.e. a level of 50% of the OEL, i.e. 0.1 regulated asbestos fibres per ml of air measured over a 4 hour period. The value at which proactive actions is required in order to control asbestos exposure to prevent exceeding the OEL. |
| Ambient Air |  | means breathable air in area of work with specific reference to breathing zone, which is defined to be a virtual area within a radius of approximately 30cm from the nose inlet. |
| Compliance Monitoring |  | means compliance sampling used to assess whether or not the personal exposure of workers to regulated asbestos fibres is in compliance with the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| OEL |  | means occupational exposure limit. |
| Parallel Measurements |  | means measurements performed in parallel, yet separately, to existing measurements to verify validity of results. |
| Safe Levels |  | means airborne asbestos exposure levels conforming to the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| Standard |  | means the Employer’s Asbestos Standard 32-303: Requirements for Safe Processing, Handling, Storing, Disposal and Phase-out of Asbestos and Asbestos Containing Material, Equipment and Articles. |
| SANAS |  | means the South African National Accreditation System. |
| TWA |  | means the average exposure, within a given workplace, to airborne asbestos fibres, normalised to the baseline of a 4 hour continuous period, also applicable to short term exposures, i.e. 10-minute TWA. |
| Z15.1 | The Employer ensures that the Ambient Air in the area where the Contractor will Provide the Services conforms to the acceptable prescribed South African standard for asbestos, as per the regulations published in GNR 155 of 10 February 2002, under the Occupational Health and Safety Act, 1993 (Act 85 of 1993) (“Asbestos Regulations”). The OEL for asbestos is 0.2 regulated asbestos fibres per millilitre of air as a 4-hour TWA, averaged over any continuous period of four hours, and the short term exposure limit of 0.6 regulated asbestos fibres per millilitre of air as a 10-minute TWA, averaged over any 10 minutes, measured in accordance with HSG248 and monitored according to HSG173 and OESSM. |  |
| Z15.2 | Upon written request by the Contractor, the Employer certifies that these conditions prevail. All measurements and reporting are effected by an independent, competent, and certified occupational hygiene inspection body, i.e. a SANAS accredited and Department of Employment and Labour approved AAIA. The Contractor may perform Parallel Measurements and related control measures at the Contractor’s expense. For the purposes of compliance the results generated from Parallel Measurements are evaluated only against South African statutory limits as detailed in clause Z15.1. Control measures conform to the requirements stipulated in the AAIA-approved asbestos work plan. |  |
| Z15.3 | The Employer manages asbestos and ACM according to the Standard. |  |
| Z15.4 | In the event that any asbestos is identified while Providing the Services, a risk assessment is conducted and if so required, with reference to possible exposure to an airborne concentration of above the AL for asbestos, immediate control measures are implemented and relevant air monitoring conducted in order to declare the area safe. |  |
| Z15.5 | The Contractor’s personnel are entitled to stop working and leave the contaminated area forthwith until such time that the area of concern is declared safe by either Compliance Monitoring or an AAIA approved control measure intervention, for example, per the emergency asbestos work plan, if applicable. |  |
| Z15.6 | The Contractor continues to Provide the Services, without additional control measures presented, on presentation of Safe Levels. The contractually agreed dates to Provide the Services, including the Completion Date, are adjusted accordingly. The contractually agreed dates are extended by the notification periods required by regulations 3 and 21 of the Asbestos Regulations, 2001. |  |
| Z15.7 | Any removal and disposal of asbestos, asbestos containing materials and waste, is done by a registered asbestos contractor, instructed by the Employer at the Employer’s expense, and conducted in line with South African legislation. |  |

# Annexure A:	 One-in-ten-year-return weather data obtained from SA Weather Bureau for [weather station]

If any one of these weather measurements recorded within a calendar month, before the Completion Date for the whole of the works and at the place stated in this Contract Data is shown to be more adverse than the amount stated below then the Contractor may notify a compensation event.

|  | Weather measurement |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Month | Cumulative rainfall (mm) | Number of days with rain more than 10mm | Number of days with min air temp < 0 deg.C | Number of days with snow lying at 08:00 CAT | [Other measurements if applicable] |
| January | [●] | [●] | [●] | [●] |  |
| February | [●] | [●] | [●] | [●] |  |
| March | [●] | [●] | [●] | [●] |  |
| April | [●] | [●] | [●] | [●] |  |
| May | [●] | [●] | [●] | [●] |  |
| June | [●] | [●] | [●] | [●] |  |
| July | [●] | [●] | [●] | [●] |  |
| August | [●] | [●] | [●] | [●] |  |
| September | [●] | [●] | [●] | [●] |  |
| October | [●] | [●] | [●] | [●] |  |
| November | [●] | [●] | [●] | [●] |  |
| December | [●] | [●] | [●] | [●] |  |

Only the difference between the more adverse recorded weather and the equivalent measurement given above is taken into account in assessing a compensation event.

C1.2 Contract Data

# Part two - Data provided by the Contractor

Notes to a tendering contractor:

- Please read both the NEC3 Engineering and Construction Contract (April 2013) and the relevant parts of its Guidance Notes (ECC3-GN) in order to understand the implications of this Data which the tenderer is required to complete.  An example of the completed Data is provided on pages 156 to 158 of the ECC3 (April 2013) Guidance Notes.

- The number of the clause which requires the data is shown in the left hand column for each statement however other clauses may also use the same data

- Where a form field like this [     is required here] appears, data is required to be inserted relevant to the option selected. Click on the form field once and type in the data.  Otherwise complete by hand and in ink.

Completion of the data in full, according to Options chosen, is essential to create a complete contract.

| ## Clause | ## Statement | ## Data |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 10.1 | The Contractor is (Name): |  |  |  |  |
|  | Address |  |  |  |  |
|  | Tel No. |  |  |  |  |
|  | Fax No. |  |  |  |  |
| 11.2(8) | The direct fee percentage is |  |  |  |  |
|  | The subcontracted fee percentage is |  |  |  |  |
| 11.2(18) | The working areas are the Site and | Offsite engineering & workshops including those of subcontractors and suppliers. |  |  |  |
| 24.1 | The Contractor's key persons are: |  |  |  |  |
|  | 1 Name: |  |  |  |  |
|  | Job: |  |  |  |  |
|  | Responsibilities: |  |  |  |  |
|  | Qualifications: |  |  |  |  |
|  | Experience: |  |  |  |  |
|  | 2 Name: |  |  |  |  |
|  | Job |  |  |  |  |
|  | Responsibilities: |  |  |  |  |
|  | Qualifications: |  |  |  |  |
|  | Experience: |  |  |  |  |
|  |  | CV's (and further key persons data including CVs) are appended to Tender Schedule entitled . |  |  |  |
| 11.2(3) | The completion date for the whole of the works is | TBC |  |  |  |
| 11.2(14) | The following matters will be included in the Risk Register | • The contractor will need to be aware that the site will be operational during construction and should provide the necessary security measures to ensure that security is not compromised. • Further risks to be identified at the initial project meeting and on an ongoing basis. • The contractor will need to be aware of the Eskom security requirements to adhere to and standards to comply with. • Conditional assessment to be conducted and accepted by Eskom representatives, prior to start on site. This includes designs. • Reputable OEM used with accredited installers, where required. |  |  |  |
| 11.2(19) | The Works Information for the Contractor’s design is in: |  |  |  |  |
| 31.1 | The programme identified in the Contract Data is |  |  |  |  |
| A | Priced contract with activity schedule |  |  |  |  |
| 11.2(21) | The activity schedule is in |  |  |  |  |
| 11.2(31) | The tendered total of the Prices is | (in figures) (in words), excluding VAT |  |  |  |
|  | ## Data for Schedules of Cost Components | Note “SCC” means Schedule of Cost Components starting on page 60, and “SSCC” means Shorter Schedule of Cost Components starting on page 63 of ECC3 (April 2013). |  |  |  |
| A | Priced contract with activity schedule | Data for the Shorter Schedule of Cost Components |  |  |  |
| 41 in SSCC | The percentage for people overheads is: | % |  |  |  |
| 21 in SSCC | The published list of Equipment is the last edition of the list published by |  |  |  |  |
|  | The percentage for adjustment for Equipment in the published list is | Minus % |  |  |  |
| 22 in SSCC | The rates of other Equipment are: | Equipment | Size or capacity |  | Rate |
| 61 in SSCC | The hourly rates for Defined Cost of design outside the Working Areas are | Category of employee |  | Hourly rate |  |
|  | Note: Hourly rates are estimated ‘cost to company of the employee’ and not selling rates. |  |  |  |  |
|  | Please insert another schedule if foreign resources may also be used |  |  |  |  |
| 62 in SSCC | The percentage for design overheads is | % |  |  |  |
| 63 in SSCC | The categories of design employees whose travelling expenses to and from the Working Areas are included in Defined Cost are: |  |  |  |  |

C1.3 Forms of Securities

# Pro forma Retention Money Guarantee (may be used when Option X16 applies)

# (to be reproduced exactly as shown below on the letterhead of the Bank providing the Guarantee)

| # Eskom Holdings SOC Limited # Megawatt Park # Maxwell Drive # Sandton # Johannesburg | # Date: |  |
| --- | --- | --- |

# Dear Sirs

# Reference No. [●] [Drafting Note: Bank reference number to be inserted]

# Retention Money Guarantee: [Drafting Note: Name of Contractor to be inserted]

# Project [  ] : Contract Reference:  [Drafting Note: Contractor contract reference number to be inserted]

# In this Guarantee the following words and expressions shall have the following meanings:-

# “Bank” - means [●], [●] Branch, (Registration No. [●]); [Drafting Note: Name of Bank to be inserted]

# “Bank’s Address” - means [●]; [Drafting Note: Bank’s physical address to be inserted]

# “Contract” – means the written agreement relating to the Project, entered into between Eskom and the Contractor, on or about the [●] day of [●] 200[●] (Contract Reference No. ………. as amended, varied, restated, novated or substituted from time to time; [Drafting Note: Signature Date and Contract reference number to be inserted]

# “Contractor” – means [●] a company registered in accordance with the laws of [●] under Registration Number [●]. [Drafting Note: Name and details of Contractor to be inserted]

# “Eskom” - means Eskom Holdings SOC Limited, a company registered in accordance with the laws of the Republic of South Africa under Registration Number 2002/015527/30

# “Expiry Date” - means the date on which the Defects Certificate is issued in terms of the Contract.

# “Guaranteed Sum” - means the sum of R [●] ([●] Rand); [Drafting Note: Insert amount of Retention Money Guarantee.].

# “Project” - means the…………………………………..

# At the instance of the Contractor, we the undersigned ______________ and ______________, in our respective capacities as _____________ and ___________ of the Bank, and duly authorized thereto, confirm that we hold the Guaranteed Sum at the disposal of Eskom, as security for the proper performance by the Contractor of all of its obligations in terms of and arising from the Contract and hereby undertake to pay to Eskom, on written demand from Eskom received prior to the Expiry Date, any sum or sums not exceeding in total the Guaranteed Sum.

# A demand for payment under this guarantee shall be made in writing at the Bank’s address and shall:

# be signed on behalf of Eskom by a director of Eskom or his authorised delegate.

# state the amount claimed (“the Demand Amount’);

# state that the Contractor has failed to carry out his obligation(s) to rectify certain defect(s) for which he is responsible under the Contract (and the nature of such defect(s)) alternatively that the Demand Amount is payable to Eskom in the circumstances contemplated in the Contract.

# Notwithstanding the reference herein to the Contract the liability of the Bank in terms hereof is as principal and not as surety and the Bank’s obligation/s to make payment:

# is and shall be absolute provided demand is made in terms of this bond in all circumstances; and

# is not, and shall not be construed to be, accessory or collateral on any basis whatsoever.

# The Bank’s obligations in terms of this Guarantee:

# shall be restricted to the payment of money only and shall be limited to the maximum of the Guaranteed Sum; and shall not be discharged and compliance with any demand for payment received by the Bank in terms hereof shall not be delayed by the fact that a dispute may exist between Eskom and the Contractor.

# Eskom shall be entitled to arrange its affairs with the Contractor in any manner which it sees fit, without advising us and without affecting our liability under this Guarantee. This includes, without

# limitation, any extensions, indulgences, release or compromise granted to the Contractor or any variation under or to the Contract.

# Should Eskom cede its rights against the Contractor to a third party where such cession is permitted under the Contract, then Eskom shall be entitled to cede to such third party the rights of Eskom under this Guarantee on written notification to the Bank of such cession.

# This Guarantee:

# shall expire on the Expiry Date until which time it is irrevocable;

# is, save as provided for in note regarding Cede of rights above, personal to Eskom and is neither negotiable nor transferable;

# shall be returned to the Bank upon the earlier of payment of the full Guaranteed Sum or expiry hereof;

# shall be regarded as a liquid document for the purpose of obtaining a court order; and

# shall be governed by and construed in accordance with the law of the Republic of South Africa and shall be subject to the jurisdiction of the Courts of the Republic of South Africa.

# Any claim which arises or demand for payment received after expiry date will be invalid and unenforceable.

# The Bank chooses domicilium citandi et executandi for all purposes in connection with this Guarantee at the Bank’s Address.

# Signed at _______________		Date ____________  Bank’s seal or stamp

# For and behalf of the Bank

# Bank Signatory: ______________		Bank Signatory: ____________

# Witness: ________________________		Witness: _________________

# Pro forma ASGI-SA Guarantee

# (to be reproduced exactly as shown below on the letterhead of the Bank providing the Guarantee)

| # Eskom Holdings Limited # Megawatt Park # Maxwell Drive # Sandton # Johannesburg | # Date: |  |
| --- | --- | --- |

# Dear Sirs

# Reference No. [●] [Drafting Note: Bank reference number to be inserted]

# Pro-Forma ASGI-SA  Guarantee: [Drafting Note: Name of Contractor to be inserted]

# Project [  ] Contract Reference: [●] [Drafting Note: Contractor contract reference number to be inserted]

# In this Guarantee the following words and expressions shall have the following meanings:-

# “Bank” - means [●], [●] Branch, (Registration No. [●]); [Drafting Note: Name of Bank to be inserted]

# “Bank’s Address” - means [●]; [Drafting Note: Bank’s physical address to be inserted]

# “Contract” – means the written agreement relating to the Project, entered into between the Employer and the Contractor, on or about the [●] day of [●] 200[●] (Contract Reference No. [●] as amended, varied, restated, novated or substituted from time to time; [Drafting Note: Signature Date and Contract reference number to be inserted]

# “Contractor” – means [●] a company registered in accordance with the laws of [●] under Registration Number [●]. [Drafting Note: Name and details of Contractor to be inserted]

# “Contractor’s ASGI-SA Obligations” – means the Contractor’s ASGI-SA Obligations under and as defined in the Contract.

# “Employer” - means Eskom Holdings Limited, a company registered in accordance with the laws of the Republic of South Africa under Registration Number 2002/015527/06.

# “Expiry Date” - means the [●] day of [●] 200[●]; [Drafting Note: anticipated date of issue of ASGI-SA Performance Certificate to be inserted.]

# “Guaranteed Sum” - means the sum of R [●] ([●] Rand);

# “Project” – means the …………………………

# At the instance of the Contractor, we the undersigned ______________ and ______________, in our respective capacities as _____________ and ___________ of the Bank, and duly authorized thereto, confirm that we hold the Guaranteed Sum at the disposal of the Employer, as security for the proper performance by the Contractor of the Contractor’s ASGI-SA Obligations and hereby undertake to pay to the Employer, on written demand from the Employer received prior to the Expiry Date, any sum or sums not exceeding in total the Guaranteed Sum.

# A demand for payment under this guarantee shall be made in writing at the Bank’s address and shall:

# state the amount claimed (“the Demand Amount’);

# state that the Demand Amount is payable to the Employer in the circumstances contemplated in the Contract.

# Notwithstanding the reference herein to the Contract the liability of the Bank in terms hereof is as principal and not as surety and the Bank’s obligation/s to make payment:

# is and shall be absolute provided demand is made in terms of this bond in all circumstances; and is not, and shall not be construed to be, accessory or collateral on any basis whatsoever.

# The Bank’s obligations in terms of this Guarantee:

# shall be restricted to the payment of money only and shall be limited to the maximum of the Guaranteed Sum; and shall not be discharged and compliance with any demand for payment received by the Bank in terms hereof shall not be delayed, by the fact that a dispute may exist between the Employer and the Contractor.

# The Employer shall be entitled to arrange its affairs with the Contractor in any manner which it sees fit, without advising us and without affecting our liability under this Guarantee. This includes, without limitation, any

# extensions, indulgences, release or compromise granted to the Contractor or any variation under or to the Contract.

# Should the Employer cede its rights against the Contractor to a third party where such cession is permitted under the Contract, then the Employer shall be entitled to cede to such third party the rights of the Employer under this Guarantee on written notification to the Bank of such cession.

# This Guarantee:

# shall expire on the Expiry Date until which time it is irrevocable;

# is, save as provided for in note regarding Cede of rights above, personal to the Employer and is neither negotiable nor transferable;

# shall be returned to the Bank upon the earlier of payment of the full Guaranteed Sum or expiry hereof;

# shall be regarded as a liquid document for the purpose of obtaining a court order; and

# shall be governed by and construed in accordance with the law of the Republic of South Africa and shall be subject to the jurisdiction of the courts of the Republic of South Africa.

# Any claim which arises or demand for payment received after expiry date will be invalid and unenforceable.

# The Bank chooses domicilium citandi et executandi for all purposes in connection with this Guarantee at the Bank’s Address.

# Signed at _____________________		Date _____________________

# For and behalf of the Bank

# Bank Signatory: ___________________	Bank Signatory: _______________

# Witness: ________________________		Witness: _________________

# Bank’s seal or stamp

# Part 2: Pricing Data

ECC3 Option A

| Document reference | Title | No of pages |
| --- | --- | --- |
| C2.1 | Pricing assumptions: Option A |  |
| C2.2 | The activity schedule |  |

- C2.1 Pricing assumptions: Option A

# How work is priced and assessed for payment

Clause 11 in NEC3 Engineering and Construction Contract, (ECC3) Option A states:

| Identified and defined terms | 11 11.2 | (20) The Activity Schedule is the activity schedule unless later changed in accordance with this contract. |
| --- | --- | --- |
|  |  | (27) The Price for Work Done to Date is the total of the Prices for each group of completed activities and each completed activity which is not in a group. A completed activity is one which is without Defects which would either delay or be covered by immediately following work. |
|  |  | (30) The Prices are the lump sum prices for each of the activities on the Activity Schedule unless later changed in accordance with this contract. |

This confirms that Option A is a lump sum form of contract where the work is broken down into activities, each of which is priced by the tendering contractor as a lump sum.   Only completed activities are assessed for payment at each assessment date; no part payment is made if the activity is not completed by the assessment date.

# Function of the Activity Schedule

Clause 54.1 in Option A states: “Information in the Activity Schedule is not Works Information or Site Information”.  This confirms that specifications and descriptions of the work or any constraints on how it is to be done are not included in the Activity Schedule but in the Works Information.  This is further confirmed by Clause 20.1 which states, “The Contractor Provides the Works in accordance with the Works Information”. Hence the Contractor does not Provide the Works in accordance with the Activity Schedule.  The Activity Schedule is only a pricing document.

# Link to the programme

Clause 31.4 states that “The Contractor provides information which shows how each activity on the Activity Schedule relates to the operations on each programme which he submits for acceptance”.  Ideally the tendering contractor will develop a high level programme first then resource each activity and thus arrive at the lump sum price for that activity both of which can be entered into the activity schedule.

# Preparing the activity schedule

Generally it is the tendering contractor who prepares the activity schedule by breaking down the work described within the Works Information into suitable activities which can be well defined, shown on a programme and priced as a lump sum.

The Employer, in his Instructions to Tenderers or in a Tender Schedule, may have listed some items that he requires the Contractor to include in his activity schedule and be priced accordingly.

It is assumed that in preparing his activity schedule the Contractor:

- Has taken account of the guidance given in the ECC3 Guidance Notes pages 19 and 20;

- Understands the function of the Activity Schedule and how work is priced and paid for;

- Is aware of the need to link the Activity Schedule to activities shown on his programme;

- Has listed and priced activities in the activity schedule which are inclusive of everything necessary and incidental to Providing the Works in accordance with the Works Information, as it was at the time of tender, as well as correct any Defects not caused by an Employer’s risk;

- Has priced work he decides not to show as a separate activity within the Prices of other listed activities in order to fulfil the obligation to complete the works for the tendered total of the Prices.

- Understands there is no adjustment to the lump sum Activity Schedule price if the amount, or quantity, of work within that activity later turns out to be different to that which the Contractor estimated at time of tender. The only basis for a change to the Prices is as a result of a compensation event.

An activity schedule could have the following format:

| Item No. | Programme Reference | Activity description | Price |
| --- | --- | --- | --- |

- C2.2 the activity schedule

Use this page as a cover page to the Contractor’s activity schedule.

# Part 3: Scope of Work

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page | 1 |
| C3.1 | Employer’s Works Information |  |
| C3.2 | Contractor’s Works Information (insert at award stage or delete if not applicable) |  |
|  | Total number of pages |  |

# C3.1: Employer’s works Information

Contents

Part 3: Scope of Work	1

C3.1: Employer’s works Information	2

1	Description of the works	5

1.1	Executive overview	5

1.2	Employer’s objectives and purpose of the works	5

1.3	Interpretation and terminology	5

2	Management and start up.	5

2.1	Management meetings	5

2.2	Documentation control	6

2.3	Health and safety risk management	6

2.4	Environmental constraints and management	6

2.5	Quality assurance requirements	6

2.6	Programming constraints	8

2.7	Contractor’s management, supervision and key people	8

2.8	Invoicing and payment	8

2.9	Insurance provided by the Employer	9

2.10	Contract change management	9

2.11	Provision of bonds and guarantees	9

2.12	Records of Defined Cost, payments & assessments of compensation events to be kept by the Contractor	9

2.13	Training workshops and technology transfer	9

3	Engineering and the Contractor’s design	10

3.1	Employer’s design	10

3.2	Parts of the works which the Contractor is to design	13

3.3	Procedure for submission and acceptance of Contractor’s design	22

3.4	Other requirements of the Contractor’s design	22

3.5	Use of Contractor’s design	22

3.6	Design of Equipment	22

3.7	Equipment required to be included in the works	22

3.8	As-built drawings, operating manuals and maintenance schedules	22

4	Procurement	23

4.1	People	23

4.1.1	Minimum requirements of people employed on the Site	23

4.1.2	BBBEE and preferencing scheme	23

4.1.3	Accelerated Shared Growth Initiative – South Africa (ASGI-SA)	24

4.2	Subcontracting	24

4.2.1	Preferred subcontractors	24

4.2.2	Subcontract documentation, and assessment of subcontract tenders	24

4.2.3	Limitations on subcontracting	24

4.2.4	Attendance on subcontractors	24

4.3	Plant and Materials	24

4.3.1	Quality	24

4.3.2	Plant & Materials provided “free issue” by the Employer	25

4.3.3	Contractor’s procurement of Plant and Materials	25

4.3.4	Spares and consumables	26

4.4	Tests and inspections before delivery	26

4.5	Marking Plant and Materials outside the Working Areas	27

4.6	Contractor’s Equipment (including temporary works).	27

4.7	Cataloguing requirements	27

5	Construction	28

5.1	Temporary works, Site services & construction constraints	28

5.1.1	Employer’s Site entry and security control, permits, and Site regulations	30

5.1.2	Restrictions to access on Site, roads, walkways and barricades	30

5.1.3	People restrictions on Site; hours of work, conduct and records	30

5.1.4	Health and safety facilities on Site	30

5.1.5	Environmental controls, fauna & flora, dealing with objects of historical interest	30

5.1.6	Title to materials from demolition and excavation	30

5.1.7	Cooperating with and obtaining acceptance of Others	30

5.1.8	Publicity and progress photographs	31

5.1.9	Contractor’s Equipment	31

5.1.10	Equipment provided by the Employer	31

5.1.11	Site services and facilities	31

5.1.12	Facilities provided by the Contractor	31

5.1.13	Existing premises, inspection of adjoining properties and checking work of Others	31

5.1.14	Survey control and setting out of the works	31

5.1.15	Excavations and associated water control	32

5.1.16	Underground services, other existing services, cable and pipe trenches and covers	32

5.1.17	Control of noise, dust, water and waste	32

5.1.18	Sequences of construction or installation	32

5.1.19	Giving notice of work to be covered up	32

5.1.20	Hook ups to existing works	32

5.2	Completion, testing, commissioning and correction of Defects	32

5.2.1	Work to be done by the Completion Date	32

5.2.2	Use of the works before Completion has been certified	32

5.2.3	Materials facilities and samples for tests and inspections	32

5.2.4	Commissioning	33

5.2.5	Start-up procedures required to put the works into operation	33

5.2.6	Take over procedures	34

5.2.7	Access given by the Employer for correction of Defects	34

5.2.8	Performance tests after Completion	34

5.2.9	Training and technology transfer	34

5.2.10	Operational maintenance after Completion	34

6	Plant and Materials standards and workmanship	35

6.1	Investigation, survey and Site clearance	35

6.2	Building works	35

6.3	Civil engineering and structural works	35

6.4	Electrical & mechanical engineering works	35

6.5	Process control and IT works	35

6.6	Other [as required]	35

7	List of drawings	35

7.1	Drawings issued by the Employer	35

C3.2	Contractor’s Works Information	37

- Description of the works

  - Executive overview

Refer to Technical Specification, document unique identifier number 474-13557, Section 1.1.

  - Employer’s objectives and purpose of the works

Refer to Technical Specification, document unique identifier number 474-13557, Section 1.2.

  - Interpretation and terminology

Refer to Technical Specification, document unique identifier number 474-13557, Section 1.3.

- Management and start up.

  - Management meetings

Regular meetings shall be convened and chaired by the Project Manager as follows:

| Title and purpose | Approximate time & interval | Location | Attendance by: |
| --- | --- | --- | --- |
| Risk register | Weekly | Eskom Academy of Learning | Employer, Contractor, Supervisor, and Designing team |
| Overall contract progress and feedback | Weekly | Eskom Academy of Learning | Employer, Contractor, Supervisor, and Designing team |
| Compensation events | When required | Eskom Academy of Learning | Employer, Contractor, Supervisor, and Designing team |
| Look ahead schedule etc | Fortnightly | Eskom Academy of Learning | Employer, Contractor, Supervisor, and Designing team |

Meetings of a specialist nature may be convened as specified elsewhere in this Works Information or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the works.  Records of these meetings shall be submitted to the Project Manager by the person convening the meeting within five days of the meeting.

All meetings shall be recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

  - Documentation control

Refer to Technical Specification, document unique identifier number 474-13557, Section 4.

  - Health and safety risk management

The Contractor shall comply with the health and safety requirements as referenced in the specification: “ERE _EAL_PV Solar & BESS_SHE Spec”.

  - Environmental constraints and management

The Contractor shall comply with the environmental criteria and constraints stated.

  - Quality assurance requirements

Refer to Technical Specification, document unique identifier number 474-13557, Sections 2.5.

  - Programming constraints

A programme showing the key activities is to be submitted with the tender documents or once appointed within two weeks. The Contractor submits a single integrated programme that incorporates all the work to be performed including that of his Subcontractors.

The interfaces between Subcontractors as well as the interfaces between Subcontractors and the Contractor are clearly identified.

Project key dates are incorporated into the programme.

All critical path items are indicated and outlined on the programme.

The order and timing of operations which the Contractor plans in order to provide the works. Strict adherence to the programme will be monitored and updated on fortnightly basis to achieve the completion dates and submitted to Eskom Project Co-ordinator. Non-conformance to the stated programme will be liable for delay damages. Any deviations on time and cost are subject to Eskom approval.

The Contractor provides the Project Programme in Microsoft Projects Format to the level 3 detail. The programme is to be updated weekly and submitted to the Project Manager for review.

  - Contractor’s management, supervision and key people

The Contractor provides the Employer with a detailed organogram of all staff and management on the contract, showing their lines of authority / communication, within two weeks of contract award. This is revised monthly and reflects any changes to the staff and management structure. The Employer reserves the right to audit and verify the structure. The Contractor has a full-time Safety and Health Officers onsite.

  - Invoicing and payment

Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice showing the amount due for payment equal to that stated in the Project Manager’s payment certificate.

The Contractor shall address the tax invoice to Eskom Holdings SOC Ltd and include on each invoice the following information:

Name and address of the Contractor and the Project Manager;

The contract number and title;

Contractor’s VAT registration number;

The Employer’s VAT registration number 4740101508;

Description of service provided for each item invoiced based on the Price List;

Total amount invoiced excluding VAT, the VAT and the invoiced amount including VAT;

(add other as required)

  - Insurance provided by the Employer

Contractor familiarises themselves with the Eskom Insurance Format A as provided in the Contract Data and make provision for all items that they are liable for.

  - Contract change management

The Employer instructs changes to the scope at any time, each instruction sets out the change and the date on which it becomes effective; and is issued to the Contractor in writing to be valid.

  - Provision of bonds and guarantees

The form in which a bond or guarantee required by the conditions of contract (if any) is to be provided by the Contractor is given in Part 1 Agreements and Contract Data, document C1.3, Sureties.

The Employer may withhold payment of amounts due to the Contractor until the bond or guarantee required in terms of this contract has been received and accepted by the person notified to the Contractor by the Project Manager to receive and accept such bond or guarantee.  Such withholding of payment due to the Contractor does not affect the Employer’s right to termination stated in this contract.

  - Records of Defined Cost, payments & assessments of compensation events to be kept by the Contractor

Not Applicable

  - Training workshops and technology transfer

Refer to Technical Specification, document unique identifier number 474-13557, Section 2.8 and Section 3.10.4.

- Engineering and the Contractor’s design

  - Contractor’s design

The Contractor design, procure, supply, install, commission, operate and maintain the PV and BES Plants. Refer to Technical Specification, document unique identifier number 474-13557.

  - Parts of the works which the Contractor is to design

Refer to Technical Specification, document unique identifier number 474-13557.

  - Procedure for submission and acceptance of Contractor’s design

Refer to Technical Specification, document unique identifier number 474-13557, Section 3 and Section 4.

  - Other requirements of the Contractor’s design

Refer to Technical Specification, document unique identifier number 474-13557.

  - Equipment required to be included in the works

Refer to Technical Specification, document unique identifier number 474-13557.

  - As-built drawings, operating manuals and maintenance schedules

Refer to Technical Specification, document unique identifier number 474-13557, Sections 3 and 4.

- Procurement

The Contractor provides the following procurement services in performing the works:

- Preparation of Employer approved supplier and Sub-Contractor’s lists for equipment and contracts to be submitted to the Employer for review and approval.

- Follows the most cost and time saving procurement strategies.

- Contract management services for the selection, appointment and management of Sub-Contractors, where required to execute the scope.

- Obtains delivery dates from Sub-Contractors and suppliers in order to realize the Completion Date;

- Receiving of invoices, verification thereof in terms of purchase orders and contract provisions, certification of invoices as being correct and payable and supply of correct invoices to the Employer

- Management of and negotiating of all suppliers and Sub-Contractors compensation events and recommendations to the Employer as to the validity, amount and payment of such events.

- Determination of penalties payable by suppliers and Sub-Contractors and recommendation to the Employer as to the enforcement of such penalties prior to any communication to suppliers and Contractors.

- Ensuring that all suppliers and Sub-Contractors, from whom the Contractor procures equipment and materials do not retain, encumber or reserve title to such items.

  - People

    - Minimum requirements of people employed on the Site

- All Contractors personnel are subjected to access control conditions as per Eskom requirements.

- All workers employed on site comply with Eskom’s health and safety standards. Workers are not allowed to be transported on the back of vans or bakkies.

- Workers are restricted to the area of activity in close proximity to the construction.

- The Contractor recruits within the immediate District Municipality for general labour/ skills to execute the project.

    - BBBEE and preferencing scheme

Contractors has a minimum BBBEE Level 6 rating after contract award.

    - Accelerated Shared Growth Initiative – South Africa (ASGI-SA)

The Contractor complies with and fulfils the Contractor’s obligations in respect of the Accelerated and Shared Growth Initiative - South Africa in accordance with and as provided for in the Contractor’s ASGI-SA Compliance Schedule stated below

[Insert the agreed ASGI-SA Compliance Schedule here]

The Contractor shall keep accurate records and provide the Project Manager with reports on the Contractor’s actual delivery against the above stated ASGI-SA criteria.   [Elaborate on access to and format of records and frequency of submission etc.]

The Contractor’s failure to comply with his ASGI-SA obligations constitutes substantial failure on the part of the Contractor to comply with his obligations under this contract.

  - Subcontracting

    - Preferred subcontractors

The Contractor notifies the Project Manager in the event of using any Sub-contractor and provides the Project Manager with a list of all sub-contractors on the project. Subcontractors cannot subcontract work to another subcontractor. The choice of the proposed sub-contractor is subject to the Project Manager’s approval before using the services of such subcontractor. The Subcontractor must be familiar with the required work and should submit CV’s of past experience and have the necessary statutory accreditations.

The Contractor provides the Project Manager with the Health and Safety plans of all the sub-contractors on the project, before commencing the project.

    - Subcontract documentation, and assessment of subcontract tenders

The Contractor uses the NEC subcontractor agreements. All subcontractor quotations for which provisional sums or budgets have been allowed, is first approved by the Employer or his representative with documentary proof. This is done well in advance of the planned scheduling of the work.

    - Limitations on subcontracting

As per Eskom requirements, subcontracting will be limited to 30% as far as possible. The Employer is notified where subcontracting exceeds the 30% threshold prior to commencement of the specific subcontracting works.

    - Attendance on subcontractors

The contractor attends to the activities of all subcontractors including direct subcontractors.

  - Plant and Materials

    - Quality

Refer to Technical Specification, document unique identifier number 474-13557.

    - Spares and consumables

Refer to Technical Specification, document unique identifier number 474-13557, Section 3.10.5.

  - Tests and inspections before delivery

Refer to Technical Specification, document unique identifier number 474-13557, Section 3.7.

## Marking Plant and Materials outside the Working Areas

All Material paid for by the Employer is clearly labelled as being the Employer’s property.

## Cataloguing requirements by the Contractor

Procurement Instruction Number 1 of 2018 – Incorporating Cataloguing into the Procurement Environment, Unique Identifier 240-1289988974 to be provided on request

- Construction

The Contractor is required to:

- Submit a comprehensive method statement of the entire works to the Project Manager for acceptance prior to the start of the works

- Submit a project specific safety file to the Employer for comments / acceptance.

- Prepare earthworks for craneage access and working rigging areas if required.

- Manage his activities on Site to ensure that no interference takes place between his work and that of others.

- Complete "Contract Activities Daily Reports".

- Liaise with the Project Manager regarding utilities and telephone facilities required for his Site establishment.

- Liaise with the Project Manager regarding the location of waste disposal sites and rubbish dumps,

- Maintain and promotes labour harmony on the Site and in the working environment.

- Immediately report any potential labour disharmony to the Project Manager.

- Not recruit or employ any personnel from the Employer and Others, without prior acceptance of the Project Manager.

- The Contractor submits a fully detailed Quality Control Plan (QCP) for acceptance within one week of the Contract Date.

- The Contractor submits a schedule of unpriced orders to be placed and this is updated regularly.

- The Contractor is responsible for defining the level of QA/QC (intervention Points) or inspection to be imposed on his Subcontractors and suppliers of material in the Quality Control Plans (QCPs). This level is based on the criticality of plant and materials and is submitted to the Employer for acceptance.

- Product data sheets and product samples are submitted for review and acceptance by the Project Manager after contract award and prior to the commencement of work.

- All quality control documentation is submitted to the Project Manager within 7 days of Contract Date.

  - Construction and Erection

- The Contractor is responsible for the design, erection, maintenance, and removal of all temporary or falsework required for the execution of the works.

- The Contractor takes all necessary precautions to ensure that none of the existing structures and services that are not in the scope of works is damaged during any demolition required. If structures and services which are not in the scope of work is damaged, the Contractor is liable to repair or replace the damaged items at their own cost.

- All construction works complies with SANS 1200 standardised specification for civil engineering construction.

  - Handover

The Contractor is responsible for the provision of a final data book.  The document contains all the relevant documentation, designs, drawings including as-built drawings, materials certificates, and product specifications on all products used, tests and results etc. which were applicable during the contract. The Contractor ensures that all relevant documentation is traceable and cross referenced where applicable.

  - Data Book

- Apart from any statutory data packages required, the Contractor also compiles a data package of the relevant drawings, test certificates etc. which he submits to the Project Manager for acceptance. These include, but are not limited to:

- Document List

- Instruction for Work/Purchase Order

- Approved ITP’s, QCP’s

- Method statements and specification adhered to

- Rigging studies (if applicable)

- Risk assessments

- Approved Drawings

- Fabrication Drawings

- Material Certificates

- Approved NDT procedure

- NDT Reports / Results

- Certificate of Manufacture

- Inspection Reports

- Corrosion Protection Consumables Certificates

- Calibration Certificates

- Notifications

- Modifications

- Concessions

- TQ’s, ER’s and communication with Employer

- Non-conformance reports

- Internal Release Notes

- Transport notifications

- Additional

- Calculations for any temporary works that may be required for the safe execution of the works.

- Concrete cube test results and reports

- Welding procedure specifications

- Welder qualifications

- Non-destructive weld test results

- Weld test certificates

- Steel grade certificates

- Concrete test results

- As-built data and drawings of the completed works upon handover. As-built drawings are submitted in PDF and native CAD formats (.DGN)

- Structural Certificate signed by the Professional Civil Engineer confirming that works have been constructed in accordance with the design.

The contents are presented in a hard cover file or files.

The data packages are prepared on a daily basis for all completed work.

Two hard copies and one soft copy of the Data Book are handed to the Employer for acceptance.

Data Books are submitted for review and acceptance before completion of the works to the Employer.

  - Temporary works, Site services & construction constraints

    - Employer’s Site entry and security control, permits, and Site regulations

The site is located in a part of an existing campus, with existing buildings all around, most buildings are currently occupied.

- The Contractor attends the Compulsory site meeting prearranged by the Employer prior to submitting tender.

- The Contractor ensures that he familiarizes himself with site conditions.

- Contractors access is limited to the areas as indicated in the scope and Contractor’s staff is prohibited from roaming in the rest of the facility.

- Eskom Holdings indemnifies themselves from any negligent events by the Contractor relating to the scope of the works within the contract period

- The Contractor, his staff and the Sub-contractors maintain identification at all times e.g. Uniforms etc.

- The Contractor is deemed to execute Safety Procedures to ensure the safety of his staff, Sub-contractors, Eskom staff during the Contract Period.

- Use of power and loud tools to be controlled and/or managed with Eskom office management team.

- The safety of the Contractors Employees, Subcontractors and building’s tenants takes preference over the scope of the works of this project.

- All site instructions to be approved and authorised in writing by the Project Manager. If this directive is not adhered to it could result in non-payment.

    - Restrictions to access on Site, roads, walkways and barricades

Access to the site

- The Employer provides the Contractor with an Access Certificate to formally provide access to the site.

- The Contractor ensures that he is familiar with conditions of access to the buildings, which includes constraints to limited parking and no goods lift is available in some of the blocks.

- The Contractor adheres to all the requirements which include, but not restricted to:

  - Identity cards with photographs

  - Cooperation in order to help Eskom provide the customer with a project schedule reflecting the period during which the construction and commissioning activities will take place.

- The Contractor will be responsible for external disputes which may occur regarding the works.

- The Contractor is when necessary or needed, required to make all the necessary arrangements with the Local Authorities via the Building Manager and or Eskom Representative.

    - People restrictions on Site; hours of work, conduct and records

Working after normal working hours and on weekends requires special permission. The Contractor shall give the Employer adequate notice if this is planned.

    - Health and safety facilities on Site

Refer to SHE specifications issued.

    - Environmental controls, fauna & flora, dealing with objects of historical interest

The Contractor shall ensure that all fauna and flora is preserved and protected during his activity on site. All such fauna and flora will be reinstated after completion of the work.

    - Title to materials from demolition and excavation

Not applicable

    - Cooperating with and obtaining acceptance of Others

Two weeks look-ahead schedule to be developed and submitted to Project Manager on a fortnight basis in order to make timeous arrangements for access into occupied buildings or areas with the occupants concerned.

    - Publicity and progress photographs

The Contractor requests approval from Project Manager for any photography and progress photographs prior to undertaking.

    - Contractor’s Equipment

The Contractor keeps an inventory of equipment brought to site. This is verified and acknowledged by Eskom security to allow removal of such equipment when required by the contractor.

Security of materials on sites:

- The Contractor provides own security on site and is held liable for excess of insurance in case of theft or loss.

Material:

- Storage and security of material is the responsibility of the Contractor until the Final Completion Certificate is certified. The Contractor is responsible for all costs involved to expedite lost, damaged or stolen material.

    - Equipment provided by the Employer

The Contractor provides all equipment and tools required to complete the works.

    - Site services and facilities

The Employer will provide power and water,

The Contractor shall make provision of waste disposal, and submit proof in a form of Waste Disposal Certificates to the Employer for approval

The Contractor shall provide everything else necessary for providing the Works.

    - Facilities provided by the Contractor

A clearly demarcated site establishment area will be provided by the Contractor for the following:

- Suitable facilities for Contractor to store all material and equipment

- Suitable facilities for his employees for changing

- Facilities for the consumption of food

- Site offices

- Toilet/Ablution facilities

- Other temporary facilities required by the Contractor

    - Existing premises, inspection of adjoining properties and checking work of Others

Contractor is to investigate existence of any services before commencement of work. Care is to be taken when Contractor is doing demolitions so as not to damage the work of others.

    - Survey control and setting out of the works

It is the Contractors responsibility to ensure accuracy when performing setting out of the works,

The Contractor shall provide adequate fastening to existing connection points.

    - Excavations and associated water control

Where excavation is required, the Contractor takes the necessary precautions not to damage any existing services.

    - Underground services, other existing services, cable and pipe trenches and covers

There is limited information regarding existing underground services

Should the need arise for the contractor to work on underground services, the Contractor is required to conduct Scanning to determine the existing/underground services and provides this information as As-Build drawings to the Employer.

    - Control of noise, dust, water and waste

The Contractor takes all precautions necessary to prevent any noise and dust whilst carrying out the work.

    - Sequences of construction or installation

Not Applicable

    - Giving notice of work to be covered up

All project communication shall be in writing.

    - Hook ups to existing works

Contractor stipulates methodology for hooking-up when working in heights and provides notification to the SHE Officer in advance and obtain permission to proceed. The Contractor cannot not hook up for lifting, supporting or for any other reason to any position or existing works in the plant without a written approval by the Project Manager.

  - Completion, testing, commissioning and correction of Defects

    - Work to be done by the Completion Date

Refer to Technical Specification, document unique identifier number 474-13557, Section 3.

    - Materials facilities and samples for tests and inspections

Refer to Technical Specification, document unique identifier number 474-13557, Section 3.

    - Commissioning

Refer to Technical Specification, document unique identifier number 474-13557, Section 3.

    - Start-up procedures required to put the works into operation

Refer to Technical Specification, document unique identifier number 474-13557, Section 3.

    - Take over procedures

Refer to Technical Specification, document unique identifier number 474-13557, Section 3.

    - Access given by the Employer for correction of Defects

The Project Manager arranges the date and access to site for the Contractor to correct defects. The Contractor updates the site safety file and the records contained inside as per construction regulations. The Contractor will be responsible for ensuring that the area is barricaded before correcting any defects.

    - Performance tests after Completion

Refer to Technical Specification, document unique identifier number 474-13557, Section 3.

    - Training and technology transfer

Refer to Technical Specification, document unique identifier number 474-13557, Section 3.

- Plant and Materials standards and workmanship

  - Investigation, survey and Site clearance

Refer to Technical Specification, document unique identifier number 474-13557

  - Building works

Refer to Technical Specification, document unique identifier number 474-13557

  - Civil engineering and structural works

Refer to Technical Specification, document unique identifier number 474-13557

  - Electrical & mechanical engineering works

Refer to Technical Specification, document unique identifier number 474-13557.

  - Process control and IT works

Refer to Technical Specification, document unique identifier number 474-13557

- List of drawings

  - Drawings issued by the Employer

Refer to Technical Specification, document unique identifier number 474-13557

# C3.2	Contractor’s Works Information

This section of the Works Information will always be contract specific depending on the nature of the works. It is most likely to be required for design and construct contracts where the tendering contractor will have proposed specifications and schedules for items of Plant and Materials and workmanship, which once accepted by the Employer prior to award of contract now become obligations of the Contractor per core clause 20.1. Typical sub headings could be a) Contractor’s design b) Plant and Materials specifications and schedules c) Other

This section could also be compiled as a separate file.

# Part 4: Site Information

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page | 1 |
| C4 | Site Information |  |
|  | Total number of pages |  |

# Part 4: Site Information

Core clause 11.2(16) states

“Site Information is information which

describes the Site and its surroundings and

is in the documents which the Contract Data states it is in.”

In Contract Data, reference has been made to this Part 4 of the contract for the location of Site Information.

# General description

Refer to Technical Specification, document unique identifier number 474-13557

# Existing buildings, structures, and plant & machinery on the Site

Refer to Technical Specification, document unique identifier number 474-13557

# Hidden services

Available information is provided at contract award.

# Other reports and publicly available information

Refer to Technical Specification, document unique identifier number 474-13557. Additional information if available id provided at contract award.

This total is required by the Employer for budgeting purposes only.  Actual amounts due will be assessed in terms of the conditions of contract.

Available from Engineering Contract Strategies Tel 011 803 3008, Fax 011 803 3009 or see www.ecs.co.za